## April.,15
PARADIP PORT TRUST
SCHEME-WISE MONITORING OF PLAN EXPENDITURE OF ANNUAL PLAN 2015-16: (FOR THE MONTH OF APRIL, 2015)
(Rs. in crores.)
Sl. No. | Name of the Scheme to be executed during 2015-16 | Date of sanction |  | Estimated Cost (Rs. in crores) |  | Anticipated Date of Completion |  | Exp. Incurred in 11th Plan, if any (upto 31.03.12) | 12th Plan outlay | Cumul. Exp. incurred upto 31.03.15 | Outlay for 2015-16 (B.E.) | Exp. in 2014-15 upto 30.04.15 | % of exp. w.r.t. outlay for 2015-16 [Col.9] | Cumul. % of exp. w.r.t. OCE/RCE [Col.4] | Overall physical progress ( in %) | Remarks
1 | 2 | 3 |  | 4 |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
|  | Original | Revised | Original | Revised | Original | Revised
A-1 | CRITICAL ON GOING SCHEME AS ON 31.03.2015
1 | Shifting of CISF complex-Construction of 'A'-type quarter | 2008-09 |  | 6.83 |  | 01.05.16 |  | 0 | 5 | 0 | 1 | 0 | 0 | 0 | -- | Work order has been issued in favour of L1 bidder on 30.04.2015.
2 | Shifting of existing 33/11KV control room at Atharabanki & 33KV power supply to BOT terminals. | 2008-09 | 2012-13 | 5 | 24.93 | 05.09.15 |  | -- | 9.51 | 2.5 | 3 | 1.0707 | 35.69 | 14.32 | 30 | Construction of 5MVA transformer room completed.33KV switch gear, 132 KV switchyard, 40MVA transfer room and other civil works are in progress.
3 | Construction of modern auditorium at Paradip Port. | 2008-09 | 2009-10 | 8.73 | 9.9981 | 30.06.12 | 30.06.15 | 2.74 | 5.5 | 3.06 | 0.3 | 0 | 0 | 30.61 | 43 | The Architectural Consultant has been disengaged due to poor performance. New drawings will be prepared with the help of NBCC. NBCC has submitted the revised estimate which is under process for approval.
4 | Railway connectivity for BOT berth. | 2008-09 |  | 89.65 |  | 04.04.16 |  | 28.6 | 45.67 | 40.98 | 5 | 0 | 0 | 45.71 | 36 | Preparatory works including field survey works have commenced.
5 | Integrated Port Information System. (PCS) | 2011-12 |  | 9.32 |  | -- |  | 0 | 10 | 0 | 0.5 | 0 | 0 | 0 | -- | The technical bids for engagement of PMC have been opened and are under evaluation.
6 | Strengthening of road inside Harbour Area | 2013-14 |  | 12.66 |  | 23.10.15 |  | 0 | -- | 0.64 | 1 | 0.2608 | 26.08 | 7.12 | 15 | Work is under execution.
7 | De-siltation of reservoir by mechanical method to shore additional volume of water during lean season including control/restriction of algae and vegetative growth so as to meet the regular crisis of water supply during lean season. | 2013-14 |  | 25.18 |  | -- |  | 0 | -- | 0 | 1 | 0 | 0 | 0 | -- | Tender has been discharged.
8 | Shore protection work to facilitate dredging of BOT Iron Ore and Coal Berth dock basin. | 2012-13 |  | 46 |  | 18.11.15 |  | 0 | 70 | 0 | 2 | 0 | 0 | 0 | -- | Work has just commenced.
9 | Capital dredging work for the Iron Ore Berth, Coal Berth and Multipurpose Berth dock basin. | 2008-09 & 2010-11 |  | 174.37 |  | -- |  | 0 | 123.85 | 0 | 5 | 0 | 0 | 0 | -- | Technical bids have been evaluated. Price bids will be opened after obtaining the security clearance.
10 | Capital dredging work for the Southern Oil Jetty dock basin. | 2012-13 |  | 48.37 |  | 31.10.14 | 31.05.15 | 0 | 48.37 | 49.59 | 2 | 0 | 0 | 102.5222 | 97 | Work is under execution.
11 | Providing net barrier around coal stackyard | 2013-14 |  | 14.03 |  | 07.10.15 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 20 | Work is in progress.
12 | Augmentation of railway facilities at Paradip | 2012-13 |  | 42 |  | -- |  | 0 | 0 | 67.22 | 5 | 0 | 0 | 160.05 | -- | This is a deposit work and is being taken up by East Coast Railway. This project envisages (i) Augmentation of station yard (ii) Construction of ROH shed and wheel lathe shed with development of CC rakes examination facilities (iii) Auto signalling of MCHP (iv) Construction of Station building, Area control, Operational offices for both Railway & Port and other allied facilities at Paradip.(v) Provision of new shunting neck at station exchange yard at Paradip.
13 | Replacement of WT-150 at IOHP | 2013-14 |  | 12.17 |  | 31.03.16 |  | 0 | 2 | 3.1 | 2 | 0 | 0 | 25.47 | 6 | Quality Assurance Plan(QAP) has been approved.
14 | Railway Electrification(OHE) | 2013-14 |  | 7.19 |  | 31.10.14 |  | 0 | 0 | 7.2 | 0.5 | 0 | 0 | 100.14 | -- | This is a deposit work to be taken up by East Coast Railway. Full amount has been deposited with E.Co. Railway to take up the work. The work is under progress.
15 | Re-routing of MCHP feeder-I & II cable | 2013-14 |  | 5.05 |  | -- |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -- | Price bids have been opened and are under evaluation.
16 | Supply, installation & commissioning of telescopic gangway (TGW) at North Oil Jetty. | 2013-14 |  | 14.61 |  | 08.04.15 | 30.03.15 | 0 | 0 | 8.07 | 5 | 0 | 0 | 55.24 | 100 | The TGW has been commissioned on 30.03.2015.
17 | Development of stackyard | -- |  | 6.16 |  | -- |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | -- | The proposal is deferred for time being. | HWD-I | WD-6
18 | Development of truck parking yard adjacent to cargil side. | -- |  | -- |  | -- |  | 0 | 0 | 0 | 0.2 | 0 | 0 | -- | -- | The proposal is deferred for time being.
19 | Development of concrete stackyard near old CISF complex. | 2013-14 |  | 46.75 |  | -- |  | 0 | 0 | 0.07 | 5 | 0 | 0 | 0.15 | -- | Survey & Soil Investigation work completed. Work order has been issued in favour of L1 bidder.
A-2 | NEW SCHEMES
1 | Development of sheds for handling of food grains | 2013-14 |  | 22.7 |  | -- |  | 0 | 0 | 0 | 2 | 5.4472 | -- | 24 | -- | In work award stage.
2 | Enhancement of draft in Central Dock basin | 2014-15 |  | 9.35 |  | 14.03.15 | 31.05.15 | 0 | 0 | 6.3 | 2 | 0 | 0 | 67.38 | 97 | Work is nearing completion.
3 | Construction of Sewarage Treatment Plant | -- |  | 84.92 |  | -- |  | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | -- | The proposal has been sent to Ministry for approval.
4 | Construction of Compound wall for new custom bonded area. | 2014-15 |  | 15.37 |  | -- |  | 0 | 0 | 0 | 0.7 | 0 | 0 | 0 | -- | Technical bids have been opened and are under evaluation.
5 | Re-alignment of water supply line for Balijhara to Sector-4, Madhuban, Nuabazar pump house. | -- |  | 10.3 |  | -- |  | 0 | 0 | 0 | 1.5 | 0 | -- | 0 | -- | The estimate has been processed for approval of Board.
6 | Installation of 2 MW Solar Power Plant | 2014-15 |  | 22 |  | -- |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | -- | Tender has been discharged due to single tender.
7 | Capital Dredging work in existing North Oil Jetty | 2013-14 |  | 16.12 |  | 06.09.15 |  | 0 | 0 | 0 | 0 | 3.4199 | -- | 21.22 | 20 | Work is under execution.
[9 empty] | 319.9 | 188.73 | 52.2 | 10.1986