## Sheet1
PARADIP PORT AUTHORITY
|  |  | PLAN EXPENDITURE UPTO 31-03-2022 | [5 empty] | (Rs. In Crores.)
SL.No. | Name of the Schemes | R.E 2021-22 | NAME OF THE WORK | WORK ORDER VALUE | DIVISION | AMOUNT PAID UPTO 31.03.21 | AMOUNT DURING THE YEAR UPTO 31.03.22 | TOTAL EXPENDITURE | BALANCE TO BE PAID {7-(9+10)} | BALANCE R.E (3-11)
1 | 2 | 3 | 5 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Integrated Port Information System | 8 | ERP | 58.01 | EDP | 29.87 | 0.93 | 0.93 | 27.21 | 7.07
2 | Capital Dredging Work for the iron ore berth, coal berth multipurpose berth. | 15 | Capital Dreging Iore berth, coal berth multipurpose berth & north BOT Dock Complex. | 76.2 | PIO | 60.4 | 15.23 | 15.23 | 0.57 | -0.23
3 | Devlopment of Stack yard | 3 | Const. of Retaining wall in the Stack Yard (MCHP). | 5.13 | HWD-1 | 0 | 0.1 | 0.27 | 5.03 | 2.73
|  |  | Upgradation of IOHP plot area. | 2.29 | HWD-1 | 1.53 | 0.17 |  | 0.59
4 | Construction of sewrage treatment Plant | 3 | Constrution supply delivery erection of 2.5 MLD at brundabana clony. | 11.92 | ECM | 11.09 | 2.35 | 7.05 | -1.52 | -4.05
|  |  | Comprehensive AMC. | 0.92 | BCD | 0.81 | 0.76 |  | -0.65
|  |  | Constrution supply delivery erection of 2.5 MLD at Bhima bhoi Colony. | 8.64 | ECM | 6.58 | 3.94 |  | -1.88
|  |  | Constrution supply delivery erection of 2.5 MLD at Trade Centre. | 10.9 | ECM | 10.45 | 0 |  | 0.45
5 | Devlopment of Concrete Roads inside Harbour area | 5 | Upgradation of the existing servicing road indside MCHP area . | 5.58 | HWD-1 | 1.94 | 6.4 | 18.73 | -2.76 | -13.73
|  |  | Four lane road from substation square to dock recreation club. | 3.96 | R & B | 2.93 | 1.79 |  | -0.76
|  |  | PMC Work for concrete road |  | HWD-1 |  | 0.43 |  | -0.43
|  |  | Stregthing of road by concrete layer L&T junction to CISF juntion. | 1.18 | HWD-1 |  | 0.27 |  | 0.91
|  |  | Cons. Of 2nd exist road fly over as port of additionalport connectivity from N. H. |  | HWD-III |  | 9.84
6 | Devlopment of Concrete Roads outside Harbour area | 4 | PMC Work for concrete road |  | PIO |  | 0.17 | 3.19 | -0.17 | 0.81
|  |  | Upgradation of road from CD plot to TATA office near Gate-3 | 6.35 | HWD-I | 5.39 | 0.02 |  | 0.94
|  |  | Stregthing of road by concrete layer from gate no. 2 via Atharabanki main gate at PPT. | 9.61 | HWD-II | 9.15 | 0.63 |  | -0.17
|  |  | Construction of four lane road from L&T junction to gate no.1. | 4.25 | PRD | 1.57 | 1.54 |  | 1.14
|  |  | Construction 2nd RCC bridge from Atharbanki square to gate no.2 . | 13.34 | PRD |  | 0.83 |  | 12.51
7 | Revamping of Existing NQ-2 Including mooring Dolphin & existing SQ | 7.2 | Extension of fertilizer berth return arm. | 7.14 | HWD-I |  | 6.87 | 7.02 | 0.27 | 0.18
|  |  | PMC"Extension of fertilizer berth in return arm". |  | HWD-I |  | 0.15 |  | -0.15
8 | Conectivity for IOHP & MCHP | 2 | PMC for design and engg. Manufacturing and supply site Installation and commisioning and PG testing extended PMC services/Const. of project mgt service for Conectivity IOHP to MCHP. | 0.99 | MCHP | 0 | 1.4 | 1.4 | -0.41 | 0.6
9 | Desalination Plant for water Supply | 0 |  |  |  |  | 0 | 0 | 0 | 0
10 | Mechanisation of EQ-1,2 & 3. | 0.5 | PMC for the work mechanisation of EQ 1,2 and 3 Berth. | 1.79 | PIO | 1.64 | 0.18 | 0.18 | -0.03 | 0.32
11 | Supply & execution of pre-cast RCC half round 200 MM Class NP-3 hume pipe inside & outside area for laying of HT Cable | 5 | construction of RCC fence for relying of H.T cable inside harbour area. | 16.87 | PED | 0 | 7.43 | 7.43 | 9.44 | -2.43
12 | Supply , instalation , testing & commissioning of scada for Mrss with other 09 substation installed different location of PPT with 5 years AMC after warranty period | 4.2 | SCADA | 4.18 | PED | 0 | 3.8 | 3.8 | 0.38 | 0.4
13 | Construction of Modern Auditorium | 0.22 |  |  |  |  | 0 | 0 | 0 | 0.22
14 | Railway Connectivity for BOT berth | 13 | Development of two new Iron berth for handling iron ore export at PPT in BOT basis. | 79.76 | PIO | 49.67 | 16.09 | 16.09 | 14 | -3.09
|  |  | Supply of sleeper | 10.69 | PIO |  | 0 |  | 10.69
15 | Supply & installation of container scanner | 3.6 | Mobile X-ray container sccaner system. | 29.68 | DTM | 14.27 | 4.1 | 4.1 | 11.31 | -0.5
| Total (A1) | 73.72 |  |  |  |  | 85.42 | 85.42 |  | -11.7
A2 | NEW SCHEMES | [8 empty] | 0
1 | Fly over Road | 5 | Const. of 2nd exist way cum Fly over Atharbanki. | 93.99 | HWD-III |  | 0 | 0.35 | 93.99 | 4.65
|  |  | Preparataion of detailed of report for cost of 2nd exist Fly over road. |  | HWD-III |  | 0.35 |  | -0.35
2 | Fly over Conectivity to MCHP over BOT tracks | 1 | Fly over Road. | 38.5 | HWD-III |  | 0 | 0 | 38.5 | 1
3 | Road with parking space & gate adjacent to BOT mery-go-round | 5 | Poviding parking place and concrete road along side of railway L&T junction to gate no. 1. | 7.45 | HWD-II |  | 8.8 | 8.8 | -1.35 | -3.8
4 | Replacement of Wagon Tippler | 15.8 | Replacement of Wagon Tippler 150 at IOHP. | 15.8 | IOHP | 0 | 14.92 | 14.92 | 0.88 | 0.88
5 | Design Fabrication Supply Erection & commissining SCR | 0.9 |  |  |  |  | 0 | 0 | 0 | 0.9
6 | Railway Upgradation work through IPRCL | 1 | Improvement post tippling Including upgradation of Auto spring point. | 1.22 |  |  | 0 | 0 | 1.22 | 1
|  |  | Upgradation of Rly track root 15. | 1.2 |  |  |  |  | 1.2
|  |  | Upgradation of main down line track fromTata level crosing to Atharbanki Bridge. | 1.69 |  |  | 0 |  | 1.69
|  |  | Track linking work between BOT down line & 15e existing siding No-18,19. | 1.74 |  |  | 0 |  | 1.74
|  |  | Const. of additional loop line at RRS 4. | 4.39 |  |  | 0 |  | 4.39
7 | Construction of Cardiac Unit at PPT Hospital | 0.01 |  |  |  |  | 0 | 0 | 0 | 0.01
| Total (A2) | 28.71 |  |  |  |  | 24.07 | 24.07 |  | 4.64
| Total (A1+A2) | 102.43 |  |  |  |  | 109.49 | 109.49 |  | -7.06
A3 | OTHER SCHEMES LESS THAN RS.5 CR. | 6.57 |  |  |  |  | 13.63 | 13.63 |  | -7.06
| G.TOTAL | 109 |  |  |  |  | 123.12 | 123.12 |  | -14.12

## Sheet2
PARADIP PORT AUTHORITY
|  | SCHEME LESS THAN RS.5 CRORE EXPENDITURE UPTO 28-02-2022 | [9 empty] | (Rs. In Crores)
SL.No. |  | Name of the Schemes | R.E 2021-22 | #REF! | NAME OF THE WORK | #REF! | WORK ORDER VALUE | DIVISION | AMOUNT PAID UPTO 31.03.21 | AMOUNT DURING THE YEAR UPTO 31.03.22 | TOTAL EXPENDITURE | BALANCE TO BE PAID {7-(9+10)} | BALANCE R.E (3-11)
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
| 1 | Misc.works to meet operational needs | 3 | 1. BHAIRAB CH. SWAIN | 4.Raising of back up area South Quay. | CEHWD-IACCTS-24/18/236 DATE-22.05.20 |  | HWD-I |  | 0.46 | 9.37 | -0.46 | -6.37
|  |  |  | 2. GRAM POWER INDIA PVT LTD | SUpply Installation Testing and commissioning of smart meter. |  |  | PED |  | 0.28 |  | -0.28
|  |  |  | 3. BIDYADHAR SWAIN | Construction of new site store building at IOHP. |  |  | HWD-III |  | 1.53 |  | -1.53
|  |  |  | 4. RITES LTD | PMC for work construction of new boys hostel. | CEHWD-III ACCTS-1/20/463 DATE-14.08.20 |  | HWD-I |  | 0.01 |  | -0.01
|  |  |  | 5. SIDDHARTH ENGG. LTD. | Construction of isolation ward inside Port Trust Hospital. |  |  | BCD |  | 0.44 |  | -0.44
|  |  |  | 6. IPRCL | Renovatrion of Old rail and repair of damage sleeper at MCHP. |  |  | PRD |  | 0.46 |  | -0.46
|  |  |  | 7. UNIQUE SERVICES PVT. LTD. | Supply Installation & Commisioning of outdoor full colour LED display. |  |  | PED |  | 0.34 |  | -0.34
|  |  |  | 8. MAGU CH. NAYAK | Constructon of new Cycolne Shelter. |  |  | BCD |  | 0.77 |  | -0.77
|  |  |  | 9. PARAKHITA CHULLI | [5 empty] | 0.21 |  | -0.21
|  |  |  | 10.MANOJ KU NAYAK | Constructon of new Conference Hall & Board room inside Adm. Building. |  |  | R&B |  | 1.26
|  |  |  | 11.CMRGS | Constructon of new Dock Counter near Gate No-III |  |  | HWD-III |  | 3.61
| 2 | 2: Modification of 11KV Distribution system; 3: 0.01; 12: 0; 13: 0.01
| 3 | 2: Replacement of EOT Crane at Junction House 2; 3: 0.35; 12: 0; 13: 0.35
| 4 | 2: Replacement of EOT Crane at Wagon Tippler.; 3: 0; 12: 0; 13: 0
| 5 | 2: Supply ,Installation Commissining of transit tower for night navigation.; 3: 0.01; 12: 0; 13: 0.01
| 6 | 2: Road alongside BOT MERY-GO.; 3: 2.7; 10: 1.31; 11: 1.31; 12: 1.31; 13: 1.39
| 7 | Realignment of 450 mm dia pipeline from Balijhara to Madhuban. | 0.5 | 1. PARIKSHIT CHULI & SONS | Realignment of 450 mm dia water supply line from new bustand near electional substation building . | CEECM ACCTS-3/20/502 DATE-02.11.20 |  | ECM |  | 1.77 | 1.77 | -1.77 | -1.27
| 8 | Renovation of protection wall & renovation of drain. | 0 | 1. BHAIRAB CH. SWAIN | Providing parking place & concrete road along 15e side Rly L&T junction to Gate no-1. | CEHWD-II/W/24/19/379 |  | HWD-II |  | 1.18 | 1.18 | -1.18 | -1.18
|  | Total | 6.57 | [6 empty] | 13.63 | 13.63 |  | -7.06
|  | No.FA/BUD/487/2021-22 | [6 empty] | Dy. C.A.O
|  | 0 | [6 empty] | Paradip Port Trust
Copy forwarded to:-
|  | 1 D.M. (M.S), PPT |  | 6 Chief Medical Officer , PPT
|  | 2 Chief Engineer , PPT |  | 7 PA to FA& CAO, PPT
|  | 3 CME , PPT |  | 8 PS to Dy.Chairman , PPT
|  | 4 Dy.Consercator, PPT |  | 9 PS to Chairman , PPT | [5 empty] | `
|  | 5 Traffic Manager, PPT |  | 10 E E (P&D) Engg Dept.
With a request to confirm the expenditure incurred as above.
With a request to confirm the expenditure incurred as above.